## Sheet1
DOTNET TRAINING AT ESSPL Status as on 16th July 2019
Day | Course Content | Assignment | Actual Date | Coverage | Milestones | Assignment submission Status
Day1 | Introduction to .Net | Environment Setup | 2019-07-06 | COMPLETE expect for ESS Coding Standard
(Weekend) | · Introduction to .Net Framework |  |  | Complete
| · Introduction to c# |  |  | Complete
| · Understanding .Net assemblies: Assemblies, different build type : console, windows, DLLs |  |  | Complete
| · Common Language Infrastructure (CLI) |  |  | Complete
| · Managed code philosophy |  |  | Complete
| · Introduction to Object Oriented Programming |  |  | Complete
| · Understanding of Visual Studio |  |  | Complete
| · Projects |  |  | Complete
| · Solutions |  |  | Complete
| · Debugging, Bookmark |  |  | Complete
| · Industry coding standard & ESS coding standard |  |  | Not Done
Day2 | Introduction to .Net |  | 2019-07-07 | COMPLETE | Quiz 1
(Weekend) | · C# Language specification: |  |  | Complete
| · Strings, Dates and time, Integers, Real numbers, Booleans |  |  | Complete
| · Performing calculations with mathematical operators |  |  | Complete
| · Converting between data types |  |  | Complete
| · Value and reference types |  |  | Complete
| · Controlling program execution |  |  | Complete
| · IF statements |  |  | Complete
| · Writing complex criteria expressions |  |  | Complete
| · CASE (switch) statements |  |  | Complete
| · For...Next, Do While...loops |  |  | Complete
| · Handling errors |  |  | Complete
| · Throwing exceptions |  |  | Complete
| · Stepping through code with the debugger |  |  | Complete
| · Try...Catch...Finally error handling |  |  | Complete
| · Commenting code |  |  | Complete
| · Basic Event handling |  |  | Complete
Day3 | Object Oriented Programming using C# | Assignmnet 1 Continues | 2019-07-12 | COMPLETE
| · Encapsulation, Abstraction, Polymorphism, Inheritance |  |  | Completed on Day 4
| · Benefit of OOPS |  |  | Complete
Day4 | Object Oriented Programming using C# | Assignmnet 1 Continues | 2019-07-15 | INCOMPLETE
| · Dividing code into classes |  |  | Complete
| · Adding fields, methods, properties, events and constructors |  |  | Incomplete
| · Defining scope and visibility |  |  | Complete
Day5 | Object Oriented Programming using C# | Assignmnet 1 Submission | 2019-07-16 | COMPLETE |  | Submitted
| · Defining classes |  |  | Complete
| · Encapsulating attributes with methods and properties |  |  | Complete
| · Providing consistent initialization using constructors |  |  | Complete
| · Overloading methods and constructors |  |  | Complete
| · Achieving reuse through inheritance and polymorphism |  |  | Complete
Day6 | Object Oriented Programming using C# |  |  | COMPLETE
| · Creating and using objects |  |  | Complete
| · Allocating object memory with new |  |  | Complete
| · Passing initial values to constructors |  |  | Complete
| · Choosing value or reference allocation |  |  | Complete
| · Invoking methods and accessing properties |  |  | Complete
| · Delegate & Events |  |  | Complete
Day7 | Object Oriented Programming using C# | Assignment 2A Submission |  |  | Quiz 2
| · Separating application responsibilities into classes |  |  | Complete
| · Single responsibility principle. |  |  | Complete
| · Inheriting a base class |  |  | Complete
| · Overriding methods in derived classes |  |  | Complete
| · Reusing code from multiple projects |  |  | Complete
| · Creating a class library in Visual Studio |  |  | Complete
| · Setting references |  |  | Complete
Day8 | Unit testing and best practices | Assignment 2B and Assignment3 Submission |  |  | Quiz 3
Day9 | ASP .Net | Assignment 3
· Version Controlling using SVN
· Industry best practices
Day10 | ASP .Net | Assignment 4
· Functioning of website
· asp .net architecture
· Challenges in website development.
Day11 | ASP .Net | Assignment 5
· Applying common Web Form controls
· Creating consistent layouts with Master Pages
Day12 | ASP .Net | Assignment 6
· Page Lifecycle,
· Event Modelling,
· Response Request server objects,
· Get-post method
Day13 | ASP .Net | Assignment 7 |  |  | Quiz 4
· State Management:
· View state
· Session state
· Application state
· Profile object
· Cookie
Day14 | ASP .Net | Assignment 8
· Page Navigations (Navigating from one page to another page through different methods and passing value from one page to another page).
Day15 | ASP .Net | Assignment 9
· User controls, Custom control, Extended controls
Day16 | ASP .Net | Assignment 10
· Application Authentication and Authorization
Day17 | ASP .Net | Assignment 11 |  |  | Quiz 5
· Integrating Ajax with existing pages
· Increasing responsiveness with Update Panel
· Triggering Ajax from outside the Update Panel
Day18 | ADO .Net | Assignment 12
· Introduction to ADO.Net
· The ADO.NET Data Providers
Day19 | ADO .Net | Assignment 12 submission |  |  | Quiz 6
· Working with Parameters
· Working with SQL Server Stored Procedures
· The Disconnected Model
· Working with the Data Adapter
· Working with the members of a Dataset
· Working with a Data View.
· Data Bindings with Web Controls.
Day20 | Refresher on JQuery, HTML DOM, CSS | Assignment 13 |  |  | Quiz 7
Day21 | ASP .Net | Assignment 13 submission
(Weekend) | · Webservices in ASP.Net Web Forms
· Usage of Webservices using JQuery
Day22 | Review | Project Discussion
Day 28 | Submission of Project